# NATIONAL CANCER INSTITUTE

## Office of Acquisitions

---

# INDEPENDENT GOVERNMENT COST ESTIMATE

## Clinical Trial Data Management Support Services

---

Solicitation Number: NCI-RFP-2026-0156

Total Estimated Value: $24,730,718 (5 Years)

Contract Type: Cost-Plus-Fixed-Fee (Term)

---

| Prepared By: | Dr. James Wilson |
| --- | --- |
| Title: | Program Manager |
| Division: | Clinical Trials Operations Program |
| Date Prepared: | January 15, 2026 |
| Version: | 1.0 |

---

### SOURCE SELECTION SENSITIVE

This document must be protected from unauthorized disclosure in accordance with FAR 15.403-3

## Document History

| Version | Date | Author | Description of Changes |
| --- | --- | --- | --- |
| 0.1 | 2026-01-05 | Dr. James Wilson | Initial labor estimates |
| 0.2 | 2026-01-10 | Dr. James Wilson | Added indirect cost rates |
| 0.3 | 2026-01-12 | Sarah Chen | Contract Specialist validation |
| 1.0 | 2026-01-15 | Dr. James Wilson | Final certified estimate |

---

## Table of Contents

1. Executive Summary (#executive-summary)

2. Labor Cost Estimate (#1-labor-cost-estimate)

3. Fringe Benefits (#2-fringe-benefits)

4. Overhead (#3-overhead)

5. Other Direct Costs (#4-other-direct-costs-odcs)

6. G&A (#5-general-and-administrative-ga)

7. Fee Calculation (#6-fee-calculation)

8. Cost Summary by Period (#7-cost-summary-by-period)

9. Total Contract Value (#8-total-contract-value)

10. Methodology (#9-methodology)

11. Assumptions (#10-assumptions)

12. Risk Considerations (#11-risk-considerations)

13. Certification (#12-certification)

## Executive Summary

| Period | Estimated Cost | Fixed Fee (8%) | Total |
| --- | --- | --- | --- |
| Base Year | $4,355,448 | $348,436 | $4,703,884 |
| Option Year 1 | $4,432,364 | $354,589 | $4,786,953 |
| Option Year 2 | $4,565,336 | $365,227 | $4,930,563 |
| Option Year 3 | $4,702,299 | $376,184 | $5,078,483 |
| Option Year 4 | $4,843,366 | $387,469 | $5,230,835 |
| Total (All Periods) | $22,898,813 | $1,831,905 | $24,730,718 |

---

## 1. Labor Cost Estimate

### 1.1 Base Year Labor

| Labor Category | Annual Hours | Hourly Rate | Extended Cost |
| --- | --- | --- | --- |
| Project Manager | 2,080 | $95.00 | $197,600 |
| Lead Data Manager | 2,080 | $82.00 | $170,560 |
| Data Manager II | 8,320 | $68.00 | $565,760 |
| Data Manager I | 12,480 | $52.00 | $648,960 |
| Senior Medical Coder | 1,040 | $75.00 | $78,000 |
| Medical Coder | 4,160 | $58.00 | $241,280 |
| QC Specialist | 2,080 | $62.00 | $128,960 |
| Database Programmer | 4,160 | $78.00 | $324,480 |
| Subtotal Direct Labor | 36,400 |  | $2,355,600 |

### 1.2 Labor Rate Basis

| Source | Weight | Notes |
| --- | --- | --- |
| GSA Schedule 874 | 40% | Professional services rates |
| Bureau of Labor Statistics | 30% | Occupational wage data |
| Historical NCI contracts | 20% | Similar scope/complexity |
| Industry surveys | 10% | Gartner, IQVIA benchmarks |

### 1.3 Escalation Factors

| Period | Escalation Rate | Basis |
| --- | --- | --- |
| Base Year | 0% | Current market rates |
| Option Year 1 | 3.0% | Historical federal contractor increases |
| Option Year 2 | 3.0% | Projected inflation |
| Option Year 3 | 3.0% | Projected inflation |
| Option Year 4 | 3.0% | Projected inflation |

---

## 2. Fringe Benefits

| Category | Base | Rate | Amount |
| --- | --- | --- | --- |
| Health Insurance | $2,355,600 | 12.0% | $282,672 |
| Retirement (401k match) | $2,355,600 | 5.0% | $117,780 |
| FICA | $2,355,600 | 7.65% | $180,203 |
| Unemployment Insurance | $2,355,600 | 1.5% | $35,334 |
| Workers Compensation | $2,355,600 | 1.0% | $23,556 |
| Paid Leave | $2,355,600 | 8.0% | $188,448 |
| Subtotal Fringe |  | 35.15% | $827,993 |

---

## 3. Overhead

| Category | Base | Rate | Amount |
| --- | --- | --- | --- |
| Facilities | $3,183,593 | 8.0% | $254,687 |
| IT Infrastructure | $3,183,593 | 5.0% | $159,180 |
| Management & Admin | $3,183,593 | 6.0% | $191,016 |
| Training & Development | $3,183,593 | 2.0% | $63,672 |
| Subtotal Overhead |  | 21.0% | $668,555 |

Base = Direct Labor + Fringe

---

## 4. Other Direct Costs (ODCs)

### 4.1 Travel

| Trip Type | Trips/Year | Days | Travelers | Per Diem | Airfare | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Monthly Meetings | 12 | 1 | 2 | $350 | $0 | $8,400 |
| Quarterly Reviews | 4 | 1 | 3 | $350 | $0 | $4,200 |
| Training Sessions | 4 | 2 | 2 | $350 | $500 | $9,600 |
| Ad-hoc Support | 6 | 1 | 1.5 | $350 | $0 | $3,150 |
| Subtotal Travel |  |  |  |  |  | $25,350 |

Note: Local travel; no airfare for most trips. Per diem based on FTR rates for Bethesda, MD.

### 4.2 Equipment and Software

| Item | Quantity | Unit Cost | Total | Notes |
| --- | --- | --- | --- | --- |
| Workstations | 20 | $1,800 | $36,000 | Amortized over 3 years |
| Monitors (dual) | 40 | $400 | $16,000 | Amortized over 3 years |
| Software Licenses | 20 | $500 | $10,000 | Annual |
| Subtotal Equipment |  |  | $62,000 |  |

Note: Equipment costs are one-time in Base Year; subsequent years include only maintenance/replacement.

### 4.3 Materials and Supplies

| Item | Annual Cost | Notes |
| --- | --- | --- |
| Office Supplies | $5,000 | Paper, toner, general supplies |
| Reference Materials | $3,000 | MedDRA/WHODrug updates, training materials |
| Telecommunications | $12,000 | Secure phone/fax lines |
| Subtotal Materials | $20,000 |  |

### 4.4 Other Direct Costs Summary

| Category | Base Year | Option 1 | Option 2 | Option 3 | Option 4 |
| --- | --- | --- | --- | --- | --- |
| Travel | $25,350 | $26,111 | $26,894 | $27,701 | $28,532 |
| Equipment | $62,000 | $15,000 | $15,450 | $15,914 | $16,391 |
| Materials | $20,000 | $20,600 | $21,218 | $21,855 | $22,510 |
| Total ODCs | $107,350 | $61,711 | $63,562 | $65,470 | $67,433 |

---

## 5. General and Administrative (G&A)

| Category | Base | Rate | Amount |
| --- | --- | --- | --- |
| G&A Expenses | $3,959,498 | 10.0% | $395,950 |

Base = Direct Labor + Fringe + Overhead + ODCs

---

## 6. Fee Calculation

| Period | Total Costs | Fee Rate | Fee Amount |
| --- | --- | --- | --- |
| Base Year | $4,355,448 | 8.0% | $348,436 |
| Option Year 1 | $4,432,364 | 8.0% | $354,589 |
| Option Year 2 | $4,565,336 | 8.0% | $365,227 |
| Option Year 3 | $4,702,299 | 8.0% | $376,184 |
| Option Year 4 | $4,843,366 | 8.0% | $387,469 |

Fee Justification: An 8% fixed fee is appropriate based on:

- Moderate technical risk

- Established contractor capabilities in clinical data management

- Well-defined requirements

- Historical fee rates for similar NCI contracts (7-9% range)

---

## 7. Cost Summary by Period

### Base Year

| Cost Element | Amount |
| --- | --- |
| Direct Labor | $2,355,600 |
| Fringe Benefits (35.15%) | $827,993 |
| Overhead (21.0%) | $668,555 |
| Other Direct Costs | $107,350 |
| G&A (10.0%) | $395,950 |
| Total Cost | $4,355,448 |
| Fixed Fee (8.0%) | $348,436 |
| Total Estimated Price | $4,703,884 |

### Option Year 1

| Cost Element | Amount |
| --- | --- |
| Direct Labor | $2,426,268 |
| Fringe Benefits (35.15%) | $852,832 |
| Overhead (21.0%) | $688,611 |
| Other Direct Costs | $61,711 |
| G&A (10.0%) | $402,942 |
| Total Cost | $4,432,364 |
| Fixed Fee (8.0%) | $354,589 |
| Total Estimated Price | $4,786,953 |

### Option Year 2

| Cost Element | Amount |
| --- | --- |
| Direct Labor | $2,499,056 |
| Fringe Benefits (35.15%) | $878,418 |
| Overhead (21.0%) | $709,269 |
| Other Direct Costs | $63,562 |
| G&A (10.0%) | $415,031 |
| Total Cost | $4,565,336 |
| Fixed Fee (8.0%) | $365,227 |
| Total Estimated Price | $4,930,563 |

### Option Year 3

| Cost Element | Amount |
| --- | --- |
| Direct Labor | $2,574,028 |
| Fringe Benefits (35.15%) | $904,771 |
| Overhead (21.0%) | $730,548 |
| Other Direct Costs | $65,470 |
| G&A (10.0%) | $427,482 |
| Total Cost | $4,702,299 |
| Fixed Fee (8.0%) | $376,184 |
| Total Estimated Price | $5,078,483 |

### Option Year 4

| Cost Element | Amount |
| --- | --- |
| Direct Labor | $2,651,249 |
| Fringe Benefits (35.15%) | $931,914 |
| Overhead (21.0%) | $752,464 |
| Other Direct Costs | $67,433 |
| G&A (10.0%) | $440,306 |
| Total Cost | $4,843,366 |
| Fixed Fee (8.0%) | $387,469 |
| Total Estimated Price | $5,230,835 |

---

## 8. Total Contract Value

| Period | Total Cost | Fee | Total Price |
| --- | --- | --- | --- |
| Base Year | $4,355,448 | $348,436 | $4,703,884 |
| Option Year 1 | $4,432,364 | $354,589 | $4,786,953 |
| Option Year 2 | $4,565,336 | $365,227 | $4,930,563 |
| Option Year 3 | $4,702,299 | $376,184 | $5,078,483 |
| Option Year 4 | $4,843,366 | $387,469 | $5,230,835 |
| Total Contract | $22,898,813 | $1,831,905 | $24,730,718 |

---

## 9. Methodology

### 9.1 Approach

This IGCE was developed using a bottom-up approach:

1. Requirements Analysis: SOW tasks decomposed into specific activities

2. Staffing Model: FTE requirements estimated per task area

3. Rate Development: Blended rate from multiple data sources

4. Indirect Cost Application: Rates consistent with DCAA audit guidelines

5. Validation: Compared against historical NCI contracts

### 9.2 Data Sources

| Source | Application |
| --- | --- |
| GSA Schedule 874 | Labor rate benchmarking |
| Bureau of Labor Statistics | Geographic wage adjustment |
| DCAA Audit Reports | Indirect cost rate validation |
| NCI Contract HHSN261201500001C | Historical cost comparison |
| NIH Contract 75N91019D00024 | Similar scope comparison |
| Federal Travel Regulations | Travel cost estimates |
| Gartner Research | Industry rate benchmarking |

### 9.3 Confidence Level

| Cost Element | Confidence | Rationale |
| --- | --- | --- |
| Direct Labor | High | Well-defined tasks, historical data |
| Fringe Benefits | High | Standard industry rates |
| Overhead | Medium | Varies by contractor |
| ODCs | High | Defined requirements |
| G&A | Medium | Varies by contractor |
| Fee | High | Standard for contract type |
| Overall | Medium-High |  |

---

## 10. Assumptions

1. Staffing Stability: Assumes minimal staff turnover; actual costs may vary with turnover-related recruiting and training.

2. Workload Volume: Based on 150 active studies; significant changes in study volume would impact costs proportionally.

3. Technology: Assumes continued use of current EDC platform (Medidata Rave); platform migration would incur additional costs.

4. Location: Assumes contractor facility within 50-mile radius of NIH Bethesda; remote work may reduce some costs.

5. Indirect Rates: Based on industry averages; actual contractor rates may differ.

6. Escalation: 3% annual escalation based on historical trends; actual may vary with economic conditions.

7. No Scope Changes: Estimate assumes no changes to SOW; modifications would require cost adjustment.

---

## 11. Risk Considerations

| Risk Factor | Impact | Mitigation |
| --- | --- | --- |
| Labor market tightness | +5-10% labor costs | Include rate escalation clauses |
| Technology changes | +/- 5% | Establish change control process |
| Workload variability | +/- 15% | Use level-of-effort contract type |
| Inflation exceeds projections | +3-5% | Annual economic adjustments |

---

## 12. Certification

I certify that this Independent Government Cost Estimate represents my best professional judgment of the fair and reasonable cost for the services described in the Statement of Work. This estimate was developed independently of any potential contractor input and is based on verifiable data sources and sound estimating methodologies.

### Prepared By

| Field | Value |
| --- | --- |
| Name | Dr. James Wilson |
| Title | Program Manager, Clinical Trials Operations |
| Organization | NCI Division of Cancer Treatment and Diagnosis |
| Date | January 15, 2026 |
| Signature | _________________________________ |

---

### Reviewed By

| Field | Value |
| --- | --- |
| Name | Sarah Chen |
| Title | Contract Specialist |
| Organization | NCI Office of Acquisitions |
| Date | January 18, 2026 |
| Signature | _________________________________ |

---

## Appendix A: Labor Rate Detail

| Labor Category | GSA Rate | BLS Rate | Historical | Blended Rate |
| --- | --- | --- | --- | --- |
| Project Manager | $98.00 | $92.00 | $94.00 | $95.00 |
| Lead Data Manager | $85.00 | $78.00 | $82.00 | $82.00 |
| Data Manager II | $72.00 | $65.00 | $68.00 | $68.00 |
| Data Manager I | $55.00 | $48.00 | $52.00 | $52.00 |
| Senior Medical Coder | $78.00 | $72.00 | $75.00 | $75.00 |
| Medical Coder | $62.00 | $55.00 | $58.00 | $58.00 |
| QC Specialist | $65.00 | $58.00 | $62.00 | $62.00 |
| Database Programmer | $82.00 | $75.00 | $78.00 | $78.00 |

---

## Appendix B: FTE Allocation by Task

| Task | PM | Lead DM | DM II | DM I | Sr Coder | Coder | QC | DB Prog | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1: Database Design | 0.1 | 0.2 | 0.5 | 0.0 | 0.0 | 0.0 | 0.1 | 1.0 | 1.9 |
| 2: Data Entry | 0.1 | 0.2 | 2.0 | 5.0 | 0.0 | 0.0 | 0.5 | 0.0 | 7.8 |
| 3: Medical Coding | 0.05 | 0.1 | 0.0 | 0.0 | 0.5 | 2.0 | 0.1 | 0.0 | 2.75 |
| 4: Database Lock | 0.1 | 0.2 | 0.5 | 0.5 | 0.0 | 0.0 | 0.2 | 0.5 | 2.0 |
| 5: Training/Doc | 0.1 | 0.1 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.2 |
| Management | 0.55 | 0.2 | 1.0 | 0.5 | 0.0 | 0.0 | 0.1 | 0.5 | 2.85 |
| Total FTE | 1.0 | 1.0 | 4.0 | 6.0 | 0.5 | 2.0 | 1.0 | 2.0 | 17.5 |

---

---

NATIONAL CANCER INSTITUTE | Office of Acquisitions

Independent Government Cost Estimate - Clinical Trial Data Management Support Services

Version 1.0 | January 15, 2026 | Page __ of __

---

Document generated by EAGLE Document Generator

Template: Independent Government Cost Estimate (IGCE)