# NATIONAL CANCER INSTITUTE

## Division of Cancer Treatment and Diagnosis

---

# STATEMENT OF WORK

## Clinical Trial Data Management Support Services

---

Solicitation Number: NCI-RFP-2026-0156

Contract Number: [To Be Assigned]

Estimated Value: $24,730,718 (5 Years)

---

| Prepared By: | Dr. James Wilson |
| --- | --- |
| Title: | Program Manager |
| Division: | Clinical Trials Operations Program |
| Date: | February 3, 2026 |
| Version: | 1.0 |

---

### SOURCE SELECTION SENSITIVE

This document contains information subject to the restrictions of FAR 3.104

## Document History

| Version | Date | Author | Description of Changes |
| --- | --- | --- | --- |
| 0.1 | 2026-01-05 | Dr. James Wilson | Initial draft |
| 0.2 | 2026-01-15 | Dr. James Wilson | Added quality metrics per COR review |
| 0.3 | 2026-01-22 | Sarah Chen | Contract Specialist review comments |
| 0.4 | 2026-01-28 | Dr. James Wilson | Security requirements updated per ISSO |
| 1.0 | 2026-02-03 | Dr. James Wilson | Final version for solicitation |

---

## Table of Contents

1. Background (#1-background)

2. Objectives (#2-objectives)

3. Scope (#3-scope)

4. Tasks (#4-tasks)

5. Deliverables Summary (#5-deliverables-summary)

6. Period of Performance (#6-period-of-performance)

7. Place of Performance (#7-place-of-performance)

8. Government Furnished Property/Information (#8-government-furnished-propertyinformation)

9. Security Requirements (#9-security-requirements)

10. Travel (#10-travel)

11. Contractor Personnel (#11-contractor-personnel)

12. Quality Assurance (#12-quality-assurance)

13. Section 508 Compliance (#13-section-508-compliance)

14. Applicable Documents (#14-applicable-documents)

15. Appendix A: Acronyms (#appendix-a-acronyms)

## 1. Background

### 1.1 Program Overview

The National Cancer Institute (NCI) Division of Cancer Treatment and Diagnosis (DCTD) oversees multiple clinical trials evaluating novel cancer therapeutics. The Clinical Trials Operations Program (CTOP) requires contractor support to manage the increasing volume and complexity of clinical trial data across approximately 150 active studies.

### 1.2 Current Environment

| Metric | Value |
| --- | --- |
| Active Studies | 150+ interventional clinical trials |
| Annual Enrollment | 12,000+ participants |
| Data Systems | Medidata Rave, REDCap, Oracle Clinical |
| Data Volume | 2.5M+ data points annually |
| Regulatory Framework | FDA 21 CFR Part 11, ICH E6(R2) GCP |

### 1.3 Strategic Objectives

This acquisition supports NCI's mission to accelerate cancer research by:

- Ensuring high-quality clinical trial data

- Maintaining regulatory compliance

- Reducing time from data collection to analysis

- Supporting timely submission of study results

---

## 2. Objectives

The contractor shall provide clinical trial data management support services to:

| # | Objective | Success Measure |

|:-:|:----------|:----------------|

| 1 | Ensure data quality across all active trials | 30 days | Monthly |

| Error rate | 80% of terms | Monthly |

| Coding accuracy | 99% on medical review | Quarterly audit |

---

### Task 4: Database Lock and Transfer

#### 4.4.1 Description

The contractor shall execute database lock procedures and prepare clean datasets for analysis and regulatory submission.

#### 4.4.2 Requirements

| Requirement | Specification |
| --- | --- |
| Pre-lock QC | 100% query resolution, coding complete |
| Lock timeline | Within 30 days of last patient, last visit |
| Dataset formats | SAS, CDISC SDTM, define.xml |
| Archive | Secured archive with audit trail preserved |

#### 4.4.3 Deliverables

| # | Deliverable | Format | Due Date |
| --- | --- | --- | --- |
| 4.1 | Database Lock Checklist | PDF | Lock - 5 days |
| 4.2 | Final Cleaned Dataset | SAS/SDTM | Lock + 5 days |
| 4.3 | Data Transfer Documentation | Word/PDF | Lock + 5 days |
| 4.4 | Archive Confirmation | PDF | Lock + 30 days |

#### 4.4.4 Performance Standards

| Metric | Target | Measurement |
| --- | --- | --- |
| Lock timeline | 30 days post-LPLV | 95% of studies |
| Dataset accuracy | Zero critical errors | Per database |
| Archive completeness | 100% documentation archived | Per database |

---

### Task 5: Training and Documentation

#### 4.5.1 Description

The contractor shall develop and maintain training materials and procedural documentation for all data management activities.

#### 4.5.2 Requirements

| Requirement | Specification |
| --- | --- |
| SOPs | Maintain current SOPs for all activities |
| Training | Annual GCP training, system-specific training |
| Documentation | Study-specific manuals and guidelines |

#### 4.5.3 Deliverables

| # | Deliverable | Format | Due Date |
| --- | --- | --- | --- |
| 5.1 | Data Management Plan Template | Word | Contract start + 30 days |
| 5.2 | Training Records | Excel/PDF | Ongoing |
| 5.3 | SOP Updates | Word/PDF | As needed |

---

## 5. Deliverables Summary

| Task | Deliverable | Format | Frequency | Approval |
| --- | --- | --- | --- | --- |
| 1 | Database packages | Various | Per study | COR |
| 2 | Status/metrics reports | Excel/PDF | Weekly/Monthly | COR |
| 3 | Coding reports | Excel | Weekly | COR |
| 4 | Lock packages | Various | Per study | COR |
| 5 | Training/SOPs | Word/PDF | As needed | COR |
| All | Monthly Progress Report | PDF | Monthly | COR |
| All | Quarterly Performance Report | PDF | Quarterly | CO/COR |

---

## 6. Period of Performance

| Period | Start Date | End Date | Duration |
| --- | --- | --- | --- |
| Base Year | 03/01/2026 | 02/28/2027 | 12 months |
| Option Year 1 | 03/01/2027 | 02/28/2028 | 12 months |
| Option Year 2 | 03/01/2028 | 02/29/2029 | 12 months |
| Option Year 3 | 03/01/2029 | 02/28/2030 | 12 months |
| Option Year 4 | 03/01/2030 | 02/28/2031 | 12 months |

---

## 7. Place of Performance

| Location | Activities |
| --- | --- |
| Contractor Facility | Primary work location for all tasks |
| NIH Campus (Bethesda, MD) | Monthly meetings, training sessions |
| Remote | Secure VPN access to NCI systems |

The contractor shall maintain a facility within 50 miles of NIH Bethesda campus for on-site meetings and emergency response.

---

## 8. Government Furnished Property/Information

### 8.1 Government Furnished Equipment (GFE)

| Item | Description |
| --- | --- |
| EDC System Access | Medidata Rave licenses (10 seats) |
| Coding Dictionaries | MedDRA and WHODrug licenses |
| VPN Access | Secure network access for contractor staff |

### 8.2 Government Furnished Information (GFI)

| Item | Description |
| --- | --- |
| Study Protocols | Final approved protocols for all active studies |
| Source Documents | CRF images, lab reports, AE narratives |
| Historical Data | Legacy study databases for reference |
| Regulatory Guidance | FDA guidance documents, NCI policies |

---

## 9. Security Requirements

### 9.1 Information Security

| Requirement | Specification |
| --- | --- |
| Data Classification | Sensitive PII, PHI (HIPAA) |
| System Security | FISMA Moderate, FedRAMP (if cloud) |
| Encryption | AES-256 at rest, TLS 1.3 in transit |
| Access Control | Role-based, principle of least privilege |

### 9.2 Personnel Security

| Position | Investigation Level |
| --- | --- |
| All contractor staff | Tier 1 (NACI) minimum |
| System administrators | Tier 2 (MBI) |
| Staff with PII access | Annual privacy training required |

### 9.3 Facility Security

- Contractor facility shall maintain SOC 2 Type II certification

- Physical access controls required for areas processing NCI data

- Annual security assessment required

---

## 10. Travel

### 10.1 Estimated Travel

| Trip Type | Frequency | Duration | Attendees |
| --- | --- | --- | --- |
| Monthly status meetings | 12/year | 1 day | 2 |
| Quarterly reviews | 4/year | 1 day | 3 |
| Training sessions | 4/year | 2 days | 2 |
| Ad-hoc (as needed) | 6/year | 1 day | 1-2 |

### 10.2 Travel Requirements

- All travel must be pre-approved by COR

- Travel shall comply with Federal Travel Regulations (FTR)

- Local travel (within 50-mile radius) not separately reimbursable

---

## 11. Contractor Personnel

### 11.1 Key Personnel

| Position | Qualifications | FTE |
| --- | --- | --- |
| Project Manager | BS + 10 years clinical data management, PMP preferred | 1.0 |
| Lead Data Manager | BS + 7 years, experience with oncology trials | 1.0 |
| Senior Medical Coder | Certified (RHIA/RHIT), 5+ years MedDRA/WHODrug | 0.5 |

### 11.2 Staffing Requirements

| Labor Category | Minimum Qualifications | Estimated FTE |
| --- | --- | --- |
| Data Manager II | BS + 5 years | 4.0 |
| Data Manager I | BS + 2 years | 6.0 |
| Medical Coder | Certification + 3 years | 2.0 |
| QC Specialist | BS + 3 years | 1.0 |
| Database Programmer | BS + 3 years, SQL/SAS | 2.0 |

### 11.3 Key Personnel Substitution

Key Personnel may not be substituted without written approval from the Contracting Officer. Proposed substitutes must have qualifications equal to or exceeding the original personnel.

---

## 12. Quality Assurance

### 12.1 Quality Control

The contractor shall implement a Quality Management System (QMS) that includes:

- Standard Operating Procedures for all activities

- Training and competency documentation

- Quality metrics and trending

- CAPA (Corrective and Preventive Action) process

- Internal audit program

### 12.2 Government Quality Assurance

The Government will conduct quality assurance through:

- Monthly metric review

- Quarterly performance assessment

- Annual comprehensive audit

- Ad-hoc reviews as warranted

### 12.3 Quality Metrics

| Metric | Target | Frequency |

|:-------|:------:|:----------|

| Data entry accuracy | 99.5% | Monthly |

| Query response time |

---

NATIONAL CANCER INSTITUTE | Division of Cancer Treatment and Diagnosis

Statement of Work - Clinical Trial Data Management Support Services

Version 1.0 | February 3, 2026 | Page __ of __

---

Document generated by EAGLE Document Generator

Template: Statement of Work (SOW)